## Sheet1
| PBV Project Timeline Template |  |  |  | KPIs | First Lease- Up Meeting | Anticipated TCO | Referral Start Date | Move-Ins Begin | Construction Completion Date | Final Referral Sent | Final Move-in Completed | All TAs Submitted | Certicate of Occupancy
| "Project Name" Start Date: | 2024-06-20 | Items in RFP template |  | Dates
# | Process Step | Date Due | Days from Dependency | Dependency
Identify Project
1 | SHRA Instructs Developer to Connect with SSF | 2024-06-27 | 7 | Start Date
2 | SSF Sends Onboarding Packet | 2024-06-23 | 3 | Start Date
3 | Developer identifies Property Managers and Service Providers | 2024-06-26 | 3 | 2
4 | Developer sets up a Kick off Lease-up meeting with all parties | 2024-07-01 | 5 | 3
Property Management sends Eligibility Checklist, over referral Numbers, project timeline, What to expect for clients.
5 | SHRA Sets up Box and Client Tracker | 2024-07-01 | 5 | 3
6 | Housing Service Provider beginss HMIS Partnership/Program Build | 2024-07-08 | 7 | 5
8 | Service Providers (HSP/BHS) Complete HMIS Training | 2024-07-15 | 14 | 5
Property Management sends Flyer about Housing Project
9 | SSF and SHRA update websites for upcoming project | 2024-07-15 | 14 | 5
Property Manangment Tells SSF when they can send referrals
Idenitfying and Prioritizing Clients
10 | SSF Selecting clients from the CoC Priority List and sending Interest letters | 2024-07-20 | 5 | 9
11 | SSF complining a waitlist of clients that meet eligbility and are interested in housing | 2024-07-22 | 2 | 10
12 | BHS Providers are creating HMIS profiles of identified clients | 2024-07-25 | 5 | 10
12 | BHS is collecting and uploading "the BASICS" in HMIS | 2024-07-23 | 1 | 11
14 |  | 2024-07-24 | 1 | 12
15 |  | 2024-07-26 | 2 | 14
16 |  | 2024-07-26 | 2 | 14
17 |  | 2024-07-27 | 1 | 16
18 |  | 2024-07-28 | 1 | 17
19 |  | 2024-07-30 | 2 | 18
21 |  | 2024-07-31 | 1 | 19
Refer Clients (on-going until Leased-up)
22 | Referrals start 120 days before the anticipated Certificate of Occupancy date | 2024-08-01 | 1 | 21
23 | Temporay Certificate of Occupancy (TCO) is facilitated by Developers (their construction) | 2024-08-07 | 7 | 21
24 | BHS sends UID of identified and Document Ready clients to SSF Staff (Required/Overreferrals) | 2024-08-08 | 1 | 23
25 | SSF Creates referral for BHS and CAS population | 2024-08-14 | 7 | 23
26 | SHRA provides combined application to the client in confirmation email | 2024-08-14 | 7 | 23
27 |  | 2024-08-21 | 14 | 23
28 |  | 2024-08-21 | 14 | 23
29 |  | 2024-08-03 | 3 | 21
Verify Client Eligibility (on-going until Leased-up)
31 | SHRA/Property pull applications from Box | 2024-08-25 | 18 | 23
32 | Applications processed by SHRA | 2024-08-27 | 2 | 32
33 | Applications processed by Property Management | 2024-08-28 | 21 | 23
34 | SHRA sends approval letters to Property Managment once Clients are approved | 2024-08-31 | 3 | 34
35 | Property Managments Updates Box with move-in date | 2024-09-07 | 7 | 36
36 | Property Management sends approval letter and schedule intake appointment with client and HSP | 2024-09-14 | 7 | 36
36 |  | 2024-09-09 | 2 | 37
37 |  | 2024-09-10 | 1 | 38
39 |  | 2024-09-13 | 3 | TBD
40 |  | 2024-09-23 | 14 | 38
Client Moves-In (on-going until Leased-up)
41 | Construction is completed | 2024-09-25 | 2 | 37
42 | Property Management send leases to SHRA | 2024-09-26 | 1 | 38
43 | SHRA signs the Tenancy Addendum | 2024-09-29 | 3 | TBD
44 | Project receives Certficate of Occupancy (CofO) | 2024-10-09 | 14 | 38
45 |  | 2024-10-10 | 14 | 38
46 |  | 2024-10-13 | 14 | 38
Formulas:
Date Due = C2+[Days from Dependency]
Date Due = [Days from Dependency]+[Date Due, row above]